## Sheet1
Task ID |  | Date started | Date finnished | Duration | Dependant on
Planning Phase
A | Complete Chart | 2025-11-11 | 2025-11-18 | 8 | -
B | Assign Tasks | 2025-11-18 | 2025-11-23 | 6 | A
C | Create Dependancy Table | 2025-11-18 | 2025-11-21 | 4 | A
D | Create CPA (Critical Path Analysis) | 2025-11-21 | 2025-11-25 | 5 | C
E | Create Flowchart | 2025-11-11 | 2025-11-18 | 8 | -
F | Pseudocode | 2025-11-18 | 2025-11-25 | 8 | E
G | File Structure and programming branch | 2025-11-18 | 2025-11-22 | 5 | A
MSB-1 | Set-Up Phase | 2025-11-25 |  |  | milestone block
H | Research JSON | 2025-11-25 | 2025-11-29 | 5 | MSB-1 | s
I | Research Random Networks | 2025-11-25 | 2025-12-02 | 8 | MSB-1
J | Create JSON File | 2025-11-29 | 2025-12-05 | 7 | H
K | Design of Rooms | 2025-12-02 | 2025-12-05 | 4 | I
L | Design of Entities | 2025-12-02 | 2025-12-05 | 4 | I
M | Create main.py | 2025-11-25 | 2025-11-28 | 4 | MSB-1
N | Create Entity class | 2025-11-28 | 2025-12-01 | 4 | M
O | Create Player class | 2025-11-28 | 2025-12-03 | 6 | M
MSB-2 | Programming Phase | 2025-12-05
P | Random room selection | 2025-12-05 | 2025-12-12 | 8 | MSB-2
Q | Random encounters | 2025-12-05 | 2025-12-19 | 15 | MSB-2
R | Inventory | 2025-12-05 | 2025-12-19 | 15 | MSB-2
S | Treasure/ Loot | 2025-12-12 | 2025-12-26 | 15 | P
T | Game Over Screen ( Hp systerm) | 2025-12-19 | 2025-12-24 | 6 | Q
U | Scoreboard ( Enemy kills) - disucss | 2025-12-24 | 2025-12-27 | 4 | T
V | Items | 2025-12-19 | 2025-12-23 | 5 | R
MSB-3 | Implementation and Testing | 2025-12-27
W | Test code | 2025-12-27 | 2026-01-03 | 8 | MSB-3
X | Unit test | 2025-12-27 | 2026-01-01 | 6 | MSB-3
Y | Debugging | 2025-12-27 | 2026-01-03 | 8 | MSB-3
Z | Reflect on new ideas | 2025-11-25 | 2025-12-23 | 29 | MSB-1
AA | Optimise code | 2025-12-27 | 2026-01-03 | 8 | MSB-3
AB | Report | 2025-12-23 | 2026-01-05 | 14 | MSB-2
AC | Submission Deadline | 2026-01-06 | 2026-01-06 | 1 | just the final task all other task have to link to
Formulas:
Date started = [Date finnished, row above]
Date started = MAX(E4:[Date finnished, row above])
Date finnished = [Date started]+7
Date finnished = [Date started]
Note on G11: Aleksander Pietras: Just a general block with a date where all the previous blocks link up to, this helps with organisation of the CPA and with work flow